| Strategic Plan Status Report (No 10) |
| --- |
| Strategic Theme: The Ilminster Economy |
| Workplan Items | Weekly Market Closer collaboration with the Local Information Centre Public Transport - new and improved bus stops, coach parking / service station, Public Transport – enabling service provision Provision of bus shelters |
| Non-Workplan |  |
| Period from: | 26 November 2019 | Period to: | 21 January 2020 |
| Overall Status |
| Previous Period (Red Amber Green): | Current Period (Red Amber Green): | Trend (Up/Down/Stable) |
| Green | Green | Stable |
| Progress since last report: |
| Concrete base works and shelter ordered Meetings with market traders and the Chamber of Commerce are being organised to discuss ideas about the market |
| Plans until next report: |
| Lease for bus shelter ground to be received from SSDC Committee agenda re attracting market stall holders |
| Risks and Issues |
| Ref | Issue / Risk Description | Mitigation Strategy/ Action Undertaken | Impact (H,M,L) | Probability (H,M,L) |
| 1 | The number of Market stallholders declines | Advertise for more stall holders | M | M |

| Strategic Plan Status Report (No 10) |
| --- |
| Strategic Theme: The Ilminster Environment |
| Workplan Items | Implementing the Open Spaces Masterplan (including Wharf Lane Rec & Britten’s Field) Cemetery - researching future need, availability of suitable land, the feasibility of developing a new cemetery; acquiring suitable land and designing new facility Protecting Herne Hill from the impact of nearby development - including obtaining designation as a local nature reserve and acquisition of additional land Encourage use of Herne Hill by providing route signage and information boards Development of a Neighbourhood Plan Improvement of the visual impact of the approach roads to the town |
| Non-Workplan | Market House roof |
| Period from: | 26 November 2019 | Period to: | 21 January 2020 |
| Overall Status |
| Previous Period (Red Amber Green): | Current Period (Red Amber Green): | Trend (Up/Down/Stable) |
| Green | Green | Stable |
| Progress since last report: |
| First draft of Neighbourhood Plan considered by Town Council First draft of Neighbourhood Plan sent to SSDC for information Quotations received for Project Manager role for Wharf Lane Rec Play area Application made for 2nd Neighbourhood Plan Grant |
| Plans until next report : |
| Herne Hill Information Boards purchased and erected Wharf Lane Rec Project Manager appointed |
| Risks and Issues |
| Ref | Issue / Risk Description | Mitigation Strategy/ Action Undertaken | Impact (H,M,L) | Probability (H,M,L) |
| 1 | Wharf Lane Rec Masterplan does not get sufficient funding | Sources of funding to be investigated | M | M |
| 2 | Work on Neighbourhood Plan does not progress | Public workshops held to get input from local people | M | H |

| Strategic Plan Status Report (No 10) |
| --- |
| Strategic Theme: Community Engagement and Governance |
| Workplan Items | Town Council Accommodation Protecting the burial / cemetery records whilst maintaining accessibility Investigate the set-up of a Community Land Trust |
| Non-Workplan | Councillor Recruitment External audit Cemetery record updates & transfers Adoption of telephone kiosk for defibrillator New leases for Tony Rice Shed and Cricket Pavilion Archie Gooch pavilion Civic events Remembrance Service Competitions and Awards Responding to external consultations Toilet Cleaning Contract Staff Recruitment Former Gooch & Housego building acquisition for community use |
| Period from: | 26 November 2019 | Period to: | 21 January 2020 |
| Overall Status |
| Previous Period (Red Amber Green): | Current Period (Red Amber Green): | Trend (Up/Down/Stable) |
| Green | Green | Stable |
| Progress since last report: |
| Interviews held for Deputy Town Clerk position |
| Plans until next report: |
| Co-option of Councillor |
| Risks and Issues |
| Ref | Issue / Risk Description | Mitigation Strategy/ Action Undertaken | Impact (H,M,L) | Probability (H,M,L) |
| 1 | Unable to appoint to Deputy Clerk Position | Review of Job Description/ person Specification and increased salary range | M | M |