| Strategic Plan Status Report (No 9) |
| --- |
| Strategic Theme: The Ilminster Economy |
| Workplan Items | Weekly Market Closer collaboration with the Local Information Centre Public Transport - new and improved bus stops, coach parking / service station, Public Transport – enabling service provision Provision of bus shelters |
| Non-Workplan |  |
| Period from: | 16 September 2019 | Period to: | 25 November 2019 |
| Overall Status |
| Previous Period (Red Amber Green): | Current Period (Red Amber Green): | Trend (Up/Down/Stable) |
| Green | Green | Stable |
| Progress since last report: |
| Agreed with SSDC location to be rented for bus shelter Costs for cement base and bus shelter obtained |
| Plans until next report: |
| Lease for bus shelter ground to be received from SSDC Order base works and shelter Item on December Resources Committee agenda re attracting market stall holders |
| Risks and Issues |
| Ref | Issue / Risk Description | Mitigation Strategy/ Action Undertaken | Impact (H,M,L) | Probability (H,M,L) |
| 1 | The number of Market stallholders declines | Advertise for more stall holders | M | M |

| Strategic Plan Status Report (No 9) |
| --- |
| Strategic Theme: The Ilminster Environment |
| Workplan Items | Implementing the Open Spaces Masterplan (including Wharf Lane Rec & Britten’s Field) Cemetery - researching future need, availability of suitable land, the feasibility of developing a new cemetery; acquiring suitable land and designing new facility Protecting Herne Hill from the impact of nearby development - including obtaining designation as a local nature reserve and acquisition of additional land Encourage use of Herne Hill by providing route signage and information boards Development of a Neighbourhood Plan Improvement of the visual impact of the approach roads to the town |
| Non-Workplan | Market House roof |
| Period from: | 16 September 2019 | Period to: | 25 November 2019 |
| Overall Status |
| Previous Period (Red Amber Green): | Current Period (Red Amber Green): | Trend (Up/Down/Stable) |
| Green | Green | Stable |
| Progress since last report: |
| Local Nature Reserve information published by Natural England Natural England “skatepark module” of Wharf Lane Rec masterplan activity trail / barrier installed Costs to implement Wharf Lane Rec Masterplan recommended by the Open Spaces Committee on the Agenda for 26 November 2019 Town Council meeting Accessible picnic bench installed in Wharf Lane Rec; Friendship Seat and new Notice Board purchased and awaiting installation; 2 further picnic benches ordered (all items made from recycled plastic) Draft Neighbourhood Plan compile including policies, to be presented to Town Council on 3 November as a draft for consultation Grounds Team started on design information for Herne Hill information boards Herne Hill Paths & Cleeves Close cut at varying heights with robotic mower |
| Plans until next report : |
| Herne Hill Information Boards purchased Draft quotation documents & obtain quotations for professional fees for Contract administrator for Wharf Lane Rec revamp |
| Risks and Issues |
| Ref | Issue / Risk Description | Mitigation Strategy/ Action Undertaken | Impact (H,M,L) | Probability (H,M,L) |
| 1 | Wharf Lane Rec Masterplan does not get sufficient funding | Sources of funding to be investigated | M | M |
| 2 | Work on Neighbourhood Plan does not progress | Public workshops held to get input from local people | M | H |

| Strategic Plan Status Report (No 9) |
| --- |
| Strategic Theme: Community Engagement and Governance |
| Workplan Items | Town Council Accommodation Protecting the burial / cemetery records whilst maintaining accessibility Investigate the set-up of a Community Land Trust |
| Non-Workplan | Councillor Recruitment External audit Cemetery record updates & transfers Adoption of telephone kiosk for defibrillator New leases for Tony Rice Shed and Cricket Pavilion Archie Gooch pavilion Civic events Remembrance Service Competitions and Awards Responding to external consultations Toilet Cleaning Contract Staff Recruitment Former Gooch & Housego building acquisition for community use |
| Period from: | 16 September 2019 | Period to: | 25 November 2019 |
| Overall Status |
| Previous Period (Red Amber Green): | Current Period (Red Amber Green): | Trend (Up/Down/Stable) |
| Green | Green | Stable |
| Progress since last report: |
| External audit completed – no actions required Assistant Grounds Manager and Admin Officer started work Deputy Clerk Position re- advertised Decision made on former Gooch & Housego building |
| Plans until next report: |
| Preparation for Quality Award Submission Recruitment of Deputy Clerk |
| Risks and Issues |
| Ref | Issue / Risk Description | Mitigation Strategy/ Action Undertaken | Impact (H,M,L) | Probability (H,M,L) |
| 1 | Unable to appoint to Deputy Clerk Position | Review of Job Description/ person Specification and increased salary range | M | M |