| No | Meeting Date and Minute Number | Topic | Resolution / Action (To Do) | Action By | Progress / Action Taken |
| --- | --- | --- | --- | --- | --- |
| 1 | 9.07.19 OS 225 | Market Town Investment Group | Dates of Meetings to be sent to Cllr James | Town Clerk | MTIG information sent out on FYI and emailed direct to Cllr James |
| 2 | 09.07.19 OS231 | Canal | Investigate TC responsibilities re the Canal Contact Environment agency re water quality & depth | Town Clerk |  |
| 3. | 09.07.19 OS233 | Britten’s Field access | Obtain prices for dropped kerb and pathway alongside football pitch | Town Clerk |  |
| 4 | 09.07.19 OS234 | Netball Court Provision | Find out about MUGA charges Get specific information of netball club requirements Get prices for marking out netball court | Town Clerk |  |
| 5 | 09.07.19 OS237 | Cemetery Grass Cutting | Raise Order for SSDCC | Town Clerk | Order sent by Email to SSDC 26.07.19 |
| 6 | 09.07.19 OS238 | Memorial Safety Testing | Raise Order for SSDCC | Town Clerk | Order sent by Email to SSDC 26.07.19 |
| 7 | 09.07.18 OS239 | Cemetery Tree Inspection | Raise Order for SSDCC | Town Clerk | Order sent by Email to SSDC 26.07.19 |
| 8 | 09.07.19 OS 240 | Cemetery Initiatives - Memorial Plant Bed | Identify location Identify plants & supplier Identify plaques and manufacturer Prepare costings and suggested charges | Town Clerk |  |
| 9 | 09.07.19 OS 240 | Cemetery Initiatives - Columbaria | Identify designs suitable for Ilminster Cemetery and costs | Town Clerk |  |
| 10 | 09.07.19 OS 241 | Grounds Maintenance Equipment - Stiga | Research Ferris Mulching capability Possibility of leasing a ride-on mower Possibility of trading in broken stiga | Town Clerk |  |
| 11 | 27.03.18 OS153 | Sponsor Signs | Write to ISCL & ITFC regarding permission for the sponsor signs | Town Clerk |  |
| 12 | OS 158 27.03.18 | Skatepark Graffiti | Investigate feasibility of running a graffiti workshop | Cllr Gunn |  |
| 13 | 23.05.17 OS89 | Dog Survey | An L shaped fence around the existing toddlers and children’s play area Town council to provide 3 extra dog bins Request 2 dog bins from SSDC Purchase “Pooh Fairy” Posters | Town Clerk | Dog bins have been ordered; ”pooh fairy” posters have been put up Dog bins have been installed. 20.02.18 SSDC will not fund two extra bins, the Town Council would have to purchase the bins and install them, would need to check SSDC capacity to empty bins before proceeding. Recommended to buy dual purpose bins. |
| 14 | 29.03.2016 OS77 | Sign Posts and Information Boards for Herne Hill | RESOLVED to proactively work with the Herne Hill Advisory Group to draft a scheme for information boards and way markers; bring back to council for approval to enable prices to be sought. | Herne Hill Advisory Group/Deputy Clerk | 19.08.16 Temporary Open Spaces Warden has started work on drafting sign-posting scheme. Potential sources of funding being explored Wood for waymarkers has been obtained via free of charge reclamation Waymakers have been purchased The Open Spaces Team have started erecting the waymark posts Waymarkers installed, noticeboards on agenda for August meeting. ITC contribution of £750 approved 22 August 2017. Grant form obtained from SSDC 19.02.18 Grant approved by SSDC, work in progress to design boards |
| 15 | 26/01/2016 OS59 | Advertising on Town Council Property | RESOLVED to defer a decision to enable a policy to be drafted for consideration at a future meeting | Town Clerk |  |
| 16 | 26.05.15 Minute 7 | Natural / Wildlife Encouragement Areas | RESOLVED (i) To regularly cut or strim the grass parallel with the Canal so that it is kept tidy (ii) That the grass on the slope from Britten’s Field towards the Ridge Path and Herne Hill should be left to grow during the summer (iii) That research is undertaken to find the most appropriate type of plants suitable for the area from Britten’s Field towards the Ridge Path and Herne Hill to encourage butterflies (iv) That research is undertaken to find the most appropriate type of plants suitable for the area from Britten’s Field towards the Ridge Path and Herne Hill which could be bought as plugs and planted to encourage further wildflower growth | Senior Open Spaces Warden | Area of slope is approx. 3 ¼ acres. Advice sought from ITC Plant supplier: Would need to clear any area for planting of existing growth and then rotovate before planting. Plugs and seeds are available, supplier suggested seed would be the best option and best to implement over a period of 2-4 years. Sept 2019 OS Chair discussing possibilities with Greener Ilminster Group |
| 17 | Town Council 30.07.13 | Market Town Investment Group | RESOLVED that: that the Council makes a contribution to the Portas Project Proposal (based on the themes of Town Image and Community Facelift) and recognises that such contributions can be work in kind. that the Town Council develops a sponsorship policy. that the Town Council actively seeks sponsorship from businesses in the town. that the Town Council recognises the proposal will require on-going resources to be provided e.g. labour and finance. |  | 1) Flower Troughs on Canal Way put in place mid June 2014. 2) Flower Troughs on Strawberry Bank put in place beginning July 2014 3) Summer and Winter planting of flower troughs on Strawberry Bank to be planted by SSDC in 2015/2016 4) Sponsorship Policy agreed 5) Belfast Sinks still to be refurbished by SSDC 19.08.16 Flower troughs now retrieved from SSDC; Belfast Sinks will be collected from Strawberry Bank by ITC Open Spaces in order to assess condition. MTIG Rep requested to ascertain current situation regarding landscaping of roundabouts, the Triangle and the top of North Street. |